## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | AUTOMATED PHRASE MINING AND IDENTIFYING SENTENCE BETWEEN ACTIVE AND PASSIVE USING NEURAL NETWORK
PROJECT GUIDE | Pallavi Maam
PROJECT MEMBERS | Indira H.K ,Deepika .B, Chandana chowdhary,Anusha .v
DATE | 2019-09-21 |  |  |  | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  |  | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Topic and Paper selection
1.1 | Basis | indira h.k | 2019-09-21 | 20%
1.1.1 | Collecting the paper | chandana | 2019-09-21 | 30%
1.2 | Research | deepika | 2019-09-21 | 40%
1.3 | Referring the paper | Anusha | 2019-09-21 | 50%
1.4 | Abstraction | indira,chandana | 2019-09-17 | 70%
1.5 | Literature servey | deepika, Anusha | 2019-09-18 | 60%
2 | Analysis on neural network
2.1 | About | Anusha | 2019-10-02 | 15%
2.2 | scope | chandana | 2019-10-02 | 30%
2.3 | Process | Deepika | 2019-10-02 | 40%
2.4 | Technics | Indira | 2019-10-02 | 60%
3 | Lexical Classifier
3.1 | Description | Anusha,indira | 2019-10-10 | 50%
3.2 | Working | chandana,indira,deepika | 2019-10-10 | 30%
3.2.1 | Uses | deepika, Anusha | 2019-10-10 | 40%
3.2.2 | Implemented | Indira,deepika | 2019-10-10 | 50%
3.3 | Model | Anusha,chandana | 2019-10-10 | 10%
4 | English Dictionary API'S
4.1 | Analysis | Anusha , chandana | 2019-10-13 | 30%
5 | UI
5.1 | Swing and applets | deepika,indira | 2019-10-15 | 50%
6 | SRS
6.1 | Swing and applets | Anusha,deepika,chandana,indira | 2019-10-23 | 50%
7 | Software specification | Anusha,chandana,deepika,indira | 2019-11-02
8 | Base Paper | Anusha,chandana,deepika,indira | 2019-11-04
10 | User Interface | Anusha,chandana,deepika,indira | 2019-11-21
11 | Pos Tagging | Anusha,chandana,deepika,indira | 2019-12-12
12 | Preprocessing | Anusha,chandana,deepika,indira | 2019-01-03
13 | Project review |  | 2019-03-10
14
15
16

## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.